## BRD vs build
Sl No. | BRD module | BRD section | Requirement | Status | What exists today | Gap / work needed
1 | Channels | Scope / Channel | Slack connector, live | Built | app/channels/slack.py; Socket Mode; verified end to end in the Sysfore workspace. | Add the sender-email lookup (see below).
2 | Channels | Scope / Channel | Microsoft Teams connector live | Partial | app/channels/teams.py: webhook, token check, acknowledge-then-reply, offline tests. | Azure Bot registration, HTTPS address, sideloading, test in a real tenant.
3 | Channels | Scope / Channel | Google Chat connector live | Partial | app/channels/gchat.py: signed-token check, both event formats, 25 s guard, offline tests. | Google Workspace app, HTTPS address, real test.
4 | Channels | Scope / Channel | Web UI connector | Partial | streamlit_app.py calls /chat and /conversations. | Not a managed channel in the admin panel; no user sign-in, so no identity for permissions.
5 | Channels | Scope | One answering core for every channel | Built | channels/core.py handle() -> chat_service.chat(); Envelope is platform-neutral.
6 | Channels | Functional / Channel | Channel type, credentials (write-only), enabled, status fields | Built | Admin Channels screen; forms generated from each adapter's SPEC; encrypted secrets; Running / Off / Not running / Not set up.
7 | Channels | Functional / Channel | Display Name field | Not built | None. One entry per platform (type is the key). | Decide: keep one per platform, or allow several of the same type (BRD wording implies several).
8 | Channels | Functional / Channel | Allowed groups (Slack channels, Teams tenants, Google Chat spaces) | Built | allowed_channels, allowed_tenants, allowed_spaces fields.
9 | Channels | Functional / Channel | Knowledge Bases lookup (required, multiple) | Not built | No knowledge-base entity exists. | Depends on the Knowledge pipeline module.
10 | Channels | Functional / Channel | Save tests and starts the channel first; bad credential never stops a working one | Built | ChannelManager.apply + admin save flow; tested.
11 | Channels | Functional / Channel | Slack outbound only; Teams and Google Chat need public HTTPS | Built | Socket Mode; start.ps1 -Tunnel opens a tunnel (untested live).
12 | Channels | Functional / Channel | DMs and @mentions, threaded reply, sources under answer | Built | Slack adapter; Teams and Google Chat adapters implement the same.
13 | Channels | Integrations | Look up the sender's email (Slack users.info, Graph for Teams, event email for Google Chat) | Not built | Not built. The Slack app has only app_mentions:read, chat:write, im:history, im:read. | Add Slack users:read + users:read.email and re-install; Graph app permission with admin consent for Teams.
14 | Channels | Functional / Channel | Test connection per channel | Built | Slack auth.test, Teams token request, Google Chat certificate reachability.
15 | Admin panel and roles | Scope | Manage channels, admins, users and roles from one page | Partial | Channels, Audit log, Admins, Account screens built. | Users and roles beyond admins; Departments.
16 | Admin panel and roles | Functional / User | Admin accounts: add, remove, last-admin protection | Built | app/admin/users.py + Admins screen + CLI.
17 | Admin panel and roles | Functional / User | Local sign-in, lockout, 8 h sessions, CSRF, HttpOnly cookie | Built | app/admin/auth.py + api.py; 55 tests. | BRD is silent on SSO; Entra ID sign-in not built.
18 | Admin panel and roles | Roles | Roles Admin, Editor, Viewer | Not built | AdminUser.role column exists but only 'admin' is ever used and nothing checks it. | Role model, per-role permissions.
19 | Admin panel and roles | Functional / User | User record: name, role, department, status Active/Deactivated, last sign-in | Partial | Email, role, provider, created_at only. | Name, department, status, last sign-in, deactivate.
20 | Admin panel and roles | Roles & Responsibilities | Users & Roles screen: add, edit, deactivate, assign role and department | Partial | Add and remove admins only. | Edit, deactivate, role and department assignment.
21 | Admin panel and roles | Functional / User | API checks role on every request; screens hidden by role | Not built | Every admin endpoint requires an admin session; no role logic. | Role checks on the API; role-aware screens.
22 | Admin panel and roles | Functional / Department | Departments (editors, retention days, banned topics, default flag) | Not built | No department entity. | New entity and screen.
23 | Admin panel and roles | Functional / Department | Map sender to department by email; default department fallback | Not built | No sender identity beyond the platform's user ID. | Needs the email lookup above plus Users and Departments.
24 | Admin panel and roles | Audit | Audit: sign-ins, failed sign-ins, config changes, secrets never logged | Built | audit_log table; Audit screen; tested that secrets never appear. | Filters (user, action, date) are not built; screen shows the latest 200.
25 | Admin panel and roles | Audit | Audit: prompt versions, document uploads/access changes, exports, retention deletions | Not built | Those features do not exist yet. | Add as each feature is built.
26 | Admin panel and roles | Functional / Document Permissions | Document permissions (Visible To, people/groups, Managed By) | Not built | None. | Entity, Groups definition, screen.
27 | Admin panel and roles | Functional / Document Permissions | Access stored in every chunk; retrieval filters by the asker | Not built | Chunk metadata holds source, doc_id, page only. Retrieval has no user context. | Metadata schema, per-store filters, identity plumbing.
28 | Admin panel and roles | Functional / Document Permissions | Only Admins and Editors can upload or delete documents | Not built | No upload at all (files are copied into a folder by a developer). | Upload screen with role checks.
29 | LLM providers | Scope / LLM | Providers: Anthropic, Google, Azure OpenAI, Grok, OpenAI, DeepSeek | Partial | One OpenAI-compatible client (langchain-openai). Gemini works through its compatible endpoint; others only if they offer one, set in .env. | Provider adapters, admin screen.
30 | LLM providers | Functional / LLM Provider | Provider record with write-only key, tested before saving | Partial | Encryption/secret store exists for channels and is reusable. The LLM key is a plaintext line in .env. | Provider entity and screen.
31 | LLM providers | Functional / LLM Provider | Available models filled from the provider after a test; connection status | Not built | None.
32 | LLM providers | Functional / Model Settings | Preferred model and a fallback model; request timeout | Not built | One model from .env. When its credit ran out (HTTP 402) the bot stopped answering. | Fallback chain and timeout; this directly fixes the incident.
33 | LLM providers | Functional / Model Settings | Fallback on 402, 429, 5xx, timeout; no retry on invalid request | Not built | None.
34 | LLM providers | Functional / Model Settings | Tokens and cost recorded per call; Usage & Cost screen | Not built | None. | Usage table, price table (who maintains it is undefined), screen.
35 | Prompts and guardrails | Scope / Prompts | Locked base prompt set by Admin | Partial | A base prompt exists (identity, scope, untrusted-context rules) but is hard-coded in app/rag.py. | Store in database, Admin-only editing.
36 | Prompts and guardrails | Functional / Prompt | Department prompts; assembly base + department + priority line | Not built | None.
37 | Prompts and guardrails | Workflow | Draft / Published / Archived versions, preview with a test question, rollback | Not built | None.
38 | Prompts and guardrails | Functional / Guardrails | Prompt-injection check | Partial | Prompt-level defences only (model told to treat context as untrusted and ignore instructions in it). No classifier. | LLM Guard integration.
39 | Prompts and guardrails | Functional / Guardrails | Toxicity, banned topics, maximum message length | Not built | None.
40 | Prompts and guardrails | Functional / Guardrails | Personal-data masking before the LLM and storage (Presidio) | Not built | None. | Also redaction in answers.
41 | Prompts and guardrails | Functional / Guardrails | Output checks on the complete answer; blocked reply text | Not built | None. Channels already receive whole answers (the API joins the stream), so no streaming change for chat apps.
42 | Prompts and guardrails | Functional / Guardrails | Guardrail settings screen (Admin) | Not built | None.
43 | Conversation memory | Functional / Conversation | Conversations stored in a database | Not built | Per-thread text files (app/memory.py), kept forever. | Migrate to database tables.
44 | Conversation memory | Functional / Conversation | Save the question first and the answer even if cut off | Not built | Both are written only after the whole stream finishes (chat_service.chat_stream), so a cut-off reply loses the turn.
45 | Conversation memory | Functional / Conversation | Summarise older turns after the reply | Not built | Fixed window of the last 6 turns, no summary.
46 | Conversation memory | Functional / Conversation | Retention per department, daily deletion job, audited | Not built | None. | Scheduler (APScheduler) is not installed.
47 | Conversation memory | Functional / Conversation | Admin export as CSV/JSON, audited | Not built | None. | Privacy review recommended (admins reading employee chats).
48 | Conversation memory | Functional / Conversation | Conversation record: department, channel, summary, user | Partial | id, timestamps, role, content, sources only.
49 | Conversation memory | Roles | Viewers see only their own conversations | Not built | GET /conversations lists every conversation, with no authentication. | See the security finding.
50 | Knowledge pipeline | Functional / Knowledge Base | Chunking strategies: fixed, per page, by heading, semantic | Partial | Fixed recursive 900/150, changeable only through .env (global). | Strategies, per-knowledge-base setting, preview.
51 | Knowledge pipeline | Functional / Knowledge Base | Embedding model choice | Not built | Chroma's built-in MiniLM, fixed.
52 | Knowledge pipeline | Functional / Knowledge Base | Vector stores: Chroma, pgvector, Azure AI Search | Partial | Chroma only, called directly (app/retriever.py); no store interface. | Store interface, two more adapters, metadata filters in each.
53 | Knowledge pipeline | Functional / Knowledge Base | Multiple knowledge bases with inherited global defaults | Not built | One collection called 'docs'.
54 | Knowledge pipeline | Functional / Knowledge Base | Rebuild into a versioned index, keep old for rollback | Not built | ingest --reset wipes the collection.
55 | Knowledge pipeline | Functional / Knowledge Base | Delete knowledge base removes vectors, files and bindings | Not built | None.
56 | Knowledge pipeline | Functional / Knowledge Base | Multi-knowledge-base channels: merge or choose by department | Not built | None. | BRD leaves 'merge or choose' undecided.
57 | Knowledge pipeline | Functional / Document | Upload, replace, delete, re-index, status (Pending/Indexed/Failed) | Not built | Folder plus `python -m app.ingest` (or start.ps1 -Ingest); no status. | Add an 'Indexing' status.
58 | Knowledge pipeline | Functional / Document | File types: PDF, Word, Markdown, text, slides | Partial | PDF, Markdown, text. | python-docx, python-pptx parsers.
59 | Knowledge pipeline | Functional / Knowledge Base | Chunk metadata: file, page, heading path, knowledge base, allowed groups | Partial | source, doc_id, page.
60 | Knowledge pipeline | Functional / Knowledge Base | Tables and code kept whole | Not built | Plain text splitter.
61 | Knowledge pipeline | Functional / Document | Batched embedding with retries; embedding cost recorded | Not built | Local embedding, no batching/retry/cost. | Matters once API embeddings are offered.
62 | Knowledge pipeline | Current process | Router decides search vs chat and rewrites the query; cited answers (file, page) | Built | chat_service._decide, rag.py; citations tested manually.
63 | Cross-cutting (NFR, stack, alerts, reports) | NFR / Security | Secrets encrypted at rest, write-only, scrubbed from errors and logs | Built | Fernet store; tests check the database files and error messages. | LLM key is still in .env.
64 | Cross-cutting (NFR, stack, alerts, reports) | NFR / Security | Admin panel local-only; HttpOnly cookie, CSRF, lockout, 8 h sessions | Built | Built and tested. | Conflicts with Editors using the panel remotely (decision needed).
65 | Cross-cutting (NFR, stack, alerts, reports) | NFR / Security | Chat API and conversation endpoints require authentication | Not built | /chat, /conversations and DELETE /conversations/{id} are open. Through a tunnel they are reachable by anyone with the address. | URGENT: protect before any tunnel is used.
66 | Cross-cutting (NFR, stack, alerts, reports) | NFR / Privacy | Personal data masked; retention enforced per department | Not built | None.
67 | Cross-cutting (NFR, stack, alerts, reports) | NFR / Availability | Fallback LLM keeps answering | Not built | None.
68 | Cross-cutting (NFR, stack, alerts, reports) | NFR / Availability | A channel with a bad credential never stops a working one | Built | Tested.
69 | Cross-cutting (NFR, stack, alerts, reports) | NFR / Availability | Runs as a service or container and restarts automatically | Partial | start.ps1 is manual; Dockerfile and compose exist but are untested and lack the admin database and master key.
70 | Cross-cutting (NFR, stack, alerts, reports) | NFR / Performance | Google Chat replies within 25 s | Partial | 25 s guard returns a polite timeout message. | No latency budget once guardrails and fallback are added.
71 | Cross-cutting (NFR, stack, alerts, reports) | NFR / Scalability | Swap the vector store without code changes | Not built | No store abstraction.
72 | Cross-cutting (NFR, stack, alerts, reports) | NFR / Maintainability | Adapter pattern for channels, providers, embeddings, stores | Partial | Channels done (SPEC, manager). Providers, embeddings, stores not.
73 | Cross-cutting (NFR, stack, alerts, reports) | NFR / Auditability | Every config, prompt, document, export and deletion audited | Partial | Config, secrets, sign-ins, admins audited. | Rest arrives with the features.
74 | Cross-cutting (NFR, stack, alerts, reports) | NFR / Compatibility | Admin panel on desktop and mobile browsers | Built | Responsive; checked at desktop, tablet and phone widths.
75 | Cross-cutting (NFR, stack, alerts, reports) | Technology stack | FastAPI, Pydantic, Streamlit, slack-bolt, botbuilder-core, google-auth, Fernet, SQLAlchemy + SQLite, plain-JS admin page | Built | All present.
76 | Cross-cutting (NFR, stack, alerts, reports) | Technology stack | Provider libraries (langchain-anthropic, langchain-google-genai) | Not built | Only langchain-openai.
77 | Cross-cutting (NFR, stack, alerts, reports) | Technology stack | LLM Guard and Presidio | Not built | Not installed. | Memory sizing (several GB with PyTorch) untested.
78 | Cross-cutting (NFR, stack, alerts, reports) | Technology stack | python-docx, python-pptx | Not built | Not installed.
79 | Cross-cutting (NFR, stack, alerts, reports) | Technology stack | Alembic migrations | Not built | Tables are created directly with a schema-version row; no migrations. | Needed before the schema changes in later phases.
80 | Cross-cutting (NFR, stack, alerts, reports) | Technology stack | APScheduler | Not built | Not installed. | Needed for retention and health checks; also single-instance only.
81 | Cross-cutting (NFR, stack, alerts, reports) | Notifications | Alerts: fallback used, provider key failing, channel failing, indexing failed, store unreachable | Partial | Channel status shows 'Not running'. Nothing else. | Banners for the rest; consider email or chat alerts (a depleted key went unnoticed).
82 | Cross-cutting (NFR, stack, alerts, reports) | Reports & Dashboard | Usage & Cost, Guardrails, Knowledge Bases, Channels reports; filterable audit log | Partial | Channel status and a basic audit list. | Everything else with its feature.

## Summary
BRD module | Built | Partial | Not built | Total | Built or partial
Channels | 8 | 3 | 3 | 14 | 78%
Admin panel and roles | 3 | 3 | 8 | 14 | 42%
LLM providers | 0 | 2 | 4 | 6 | 33%
Prompts and guardrails | 0 | 2 | 6 | 8 | 25%
Conversation memory | 0 | 1 | 6 | 7 | 14%
Knowledge pipeline | 1 | 4 | 8 | 13 | 38%
Cross-cutting (NFR, stack, alerts, reports) | 5 | 6 | 9 | 20 | 55%
All | 17 | 21 | 44 | 82 | 46%
Basis: BRD-CAA-V1.0 (draft, 15 Oct 2026) against the repository at the current commit. 'Partial' means something real exists but it does not meet the requirement as written. Statuses are a judgement; the evidence column says why.

## Suggested order
Step | Work | Why this order | Module
1 | Close the open chat API (before any tunnel) | Require authentication on /chat and /conversations, or keep them off the tunnel. Small, and removes the main security exposure. | Cross-cutting
2 | LLM providers with fallback | Preferred + fallback model, provider screen, keys in the encrypted store. Fixes the outage already seen and unblocks cost tracking. Largely independent of other modules. | LLM providers
3 | Users, departments, roles, sender email lookup | Everything per-department (prompts, banned topics, retention, permissions) depends on this. Decide Entra SSO and remote admin access first. | Admin panel and roles
4 | Knowledge bases and documents | KB entity, upload and status, chunk metadata including allowed groups, store interface. Do the metadata schema now so permissions need no re-index later. | Knowledge pipeline
5 | Document permissions | Groups, access fields, retrieval filters, identity plumbing through the answering core. | Admin panel and roles
6 | Prompts (base + department, versions) | Needs departments and the admin screens from step 3. | Prompts and guardrails
7 | Guardrails | LLM Guard and Presidio; measure latency on the target server first; define the Google Chat time budget. | Prompts and guardrails
8 | Conversation memory in the database | Move to tables, save the question first, summaries, retention job, export. Needs departments. | Conversation memory
9 | Usage, cost, reports, alerts | Builds on provider, guardrail and memory data. | Cross-cutting
Parallel | Teams and Google Chat real-platform tests | Independent; needs a bot registration, HTTPS address and Workspace. | Channels