## Feature breakdown
Sl No. | Feature | Sub Feature | Description | Status | Area (from original list)
1 | Channel connectors | Slack | Answer DMs and @mentions in a thread using Socket Mode (outbound connection, no public URL). Verified end to end with a real workspace. | Done | Channels
2 |  | Microsoft Teams | Answer through an Azure Bot webhook with an immediate acknowledgement and a background reply. Built and tested offline; needs a bot registration, an HTTPS address and a test in a real tenant. | In Progress | Channels
3 |  | Google Chat | Answer through an HTTP endpoint, verifying Google's signed token (both event formats). Built and tested offline; needs Google Workspace, an HTTPS address and a real test. | In Progress | Channels
4 |  | Web UI (Streamlit) | Optional chat page that calls the same API as the other channels. | Done | Channels
5 | Channel management | Add / edit a channel | Settings form is generated from each adapter's own field list, so a new platform needs no UI code. | Done | Channels
6 |  | Enable / disable / delete | Switch a channel on or off or remove it, with its stored settings and secrets. | Done | Channels
7 |  | Test connection | Check entered credentials against the platform before saving (Google Chat can only confirm its signing certificates are reachable). | Done | Channels
8 |  | Apply without restart | New settings are validated and started first; if that fails, the working connection and stored settings stay untouched. | Done | Channels
9 |  | Channel status | Show Running, Off, Not running or Not set up for each platform. | Done | Channels
10 |  | Access limits | Restrict where the bot answers: allowed Slack channels, Teams tenants, Google Chat spaces. | Done | Channels
11 |  | Webhook endpoint helper | Show the endpoint path to enter at Microsoft or Google, with a copy button; start script can open a public tunnel. | Done | Channels
12 |  | Per-knowledge-base channels | Bind each channel to a knowledge base so different channels answer from different documents. | Not Started | Channels
13 |  | Real-platform verification | Run Teams and Google Chat against real accounts and record the results. | Not Started | Channels
14 | Admin accounts | Create first admin | Command-line setup with a hidden password prompt; only company-domain addresses accepted. | Done | Users, roles, permissions
15 |  | Local sign-in | Hashed passwords, signed session cookie, CSRF protection, lockout after repeated failures. | Done | Users, roles, permissions
16 |  | Add / remove admins | Manage admins on the Admins screen; cannot remove yourself or the last admin. | Done | Users, roles, permissions
17 |  | Change password | Self-service; signs out all other sessions. | Done | Users, roles, permissions
18 |  | Audit log | Record who signed in and who changed what, without secret values. | Done | Users, roles, permissions
19 | Logged role name |  | Display the signed-in user's role (today always Admin). | Done | Users, roles, permissions
20 | Roles | Multiple roles | Add roles beyond Admin, for example Editor (upload documents) and Viewer (read only). | Not Started | Users, roles, permissions
21 |  | Role-based screens | Hide and show admin screens based on the signed-in user's role. | Not Started | Users, roles, permissions
22 | Single sign-on | Microsoft Entra ID | Sign in with company accounts instead of local passwords. Needs an Entra app registration. | Not Started | Users, roles, permissions
23 | Document permissions | Who can add files | Only chosen roles can upload or delete documents. | Not Started | Users, roles, permissions
24 |  | Who can see which files | Per-document access list (people, groups or everyone). | Not Started | Users, roles, permissions
25 |  | Identity mapping | Map Slack, Teams and Google Chat users to one person and their groups. | Not Started | Users, roles, permissions
26 |  | Enforce at retrieval | Filter documents by the asker's access before anything reaches the LLM. | Not Started | Users, roles, permissions
27 | Session control | Revoke sessions | End an individual session from the admin page (today sessions end on expiry, password change or key change). | Not Started | Users, roles, permissions
28 | Credential storage | Encrypted at rest | Channel credentials are encrypted (Fernet) in the admin database; the master key comes from an environment variable. | Done | Secrets and credentials
29 |  | Write-only secrets | Never returned by the API; the UI shows 'set' and only allows replacing a value. | Done | Secrets and credentials
30 |  | Leak prevention | Secret values are scrubbed from error messages and never written to the audit log. | Done | Secrets and credentials
31 |  | Migrate from files | One-time import of existing channels.yaml and .env settings into the database. | Done | Secrets and credentials
32 | Credential lifecycle | Key rotation | Several master keys can be listed so old secrets still decrypt; a bulk re-encrypt command is still to be built. | In Progress | Secrets and credentials
33 |  | Backup and recovery | Guidance for backing up the master key and database, and what to do if the key is lost. | Done | Secrets and credentials
34 |  | Remove old plaintext | Delete the original tokens from .env once they are in the database. | Not Started | Secrets and credentials
35 |  | Expiry reminders | Warn when a stored credential is old or about to expire. | Not Started | Secrets and credentials
36 | Vault integration | Cloud key vault | Use Azure Key Vault or GCP Secret Manager for the master key through the SecretStore interface. | Not Started | Secrets and credentials
37 | Admin API | Endpoints | Sign-in, channels (create, update, test, delete), audit log and admins under /admin/api. | Done | Admin UI / API
38 | Admin page | Screens | Sign-in, Channels, Audit log, Admins and Account. | Done | Admin UI / API
39 |  | Responsive layout | Works on desktop, tablet and phone (tabs scroll, tables become cards, large tap targets). | Done | Admin UI / API
40 |  | Upcoming placeholders | Greyed-out sidebar items for Documents, Chunking, Vector store, Retrieval and LLM provider. | Done | Admin UI / API
41 | Page security | Local-only access | Refuses requests from other machines and anything arriving through a tunnel or proxy. | Done | Admin UI / API
42 |  | Browser protections | Strict content security policy, no inline scripts or HTML injection, closed cross-origin access. | Done | Admin UI / API
43 | Upcoming screens | Documents | Upload, list and set access for documents. | Not Started | Admin UI / API
44 |  | Chunking strategy | Choose how documents are split: fixed size, per page, by heading, semantic. | Not Started | Admin UI / API
45 |  | Vector store | Choose pgvector, Qdrant or Azure AI Search instead of the built-in ChromaDB. | Not Started | Admin UI / API
46 |  | Retrieval strategy | Hybrid keyword and vector search, re-ranker, query rewriting. | Not Started | Admin UI / API
47 |  | LLM provider and model | Claude, Azure, Ollama, a different model per step, and a fallback when one fails. | Not Started | Admin UI / API
48 | Deployment | Docker support | Add the master key and a volume for the admin database to docker-compose; the Docker path is untested. | Not Started | Admin UI / API
49 |  | Secure remote access | Private or HTTPS access to the admin page for hosted setups (for example IAP or VPN). | Not Started | Admin UI / API
50 | Quality | Automated tests | 55 tests cover channels, encryption, the admin API and the page's security rules. | Done | Admin UI / API

## Summary
Area | Done | In Progress | Not Started | Total
Channels | 9 | 2 | 2 | 13
Users, roles, permissions | 6 | 0 | 8 | 14
Secrets and credentials | 5 | 1 | 3 | 9
Admin UI / API | 7 | 0 | 7 | 14
All | 27 | 3 | 20 | 50